## Intro
Risk Report Data
This file is the template that the Python ReportData script will use to format its output. Go through each tab to find the relevant information for that section of the report.
Overall PWCE: |  | 0
Notes | To obtain the risk matrix used for section 5, go to the following link and take a screenshot (Snipping Tool or Win-Shift-S):
https://jira.lsstcorp.org/projects/RM?selectedItem=com.ja.jira.plugin.report.riskmanagement:RiskManagementTab

## Table 1
Risk Summary
Sub-system | Active Risk/Opportunity | Proposed | Realized | Retired | Expected Labor Risk Exposure (K-USD)* | Expected Non-Labor Risk Exposure | Prob. Weighted Exposure Cost (K-USD)* | Prob. Weighted Exposure Cost After Mitigation (K-USD)* | Subsystem | Labor Exposure | Nonlabor Exposure | PWE ($K) | PWEa ($K)
Data Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Any missing rows indicate all values are 0
Education and Public Outreach | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Any missing rows indicate all values are 0
Project Management Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Any missing rows indicate all values are 0
Systems Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Any missing rows indicate all values are 0
Telescope & Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Any missing rows indicate all values are 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Totals | 0 | 0 | 0 | 0
Subsystem

## Table 2
Opportunity Summary
Sub-system | Active Risk/Opportunity | Proposed | Realized | Retired | Expected Labor Risk Exposure (K-USD)* | Expected Non-Labor Risk Exposure | Prob. Weighted Exposure Cost (K-USD)* | Subsystem | PWE ($K)
Data Management | 0 | 0 | 0 | 0 |  |  | 0 | Any missing rows indicate all values are 0
Education and Public Outreach | 0 | 0 | 0 | 0 |  |  | 0 | Any missing rows indicate all values are 0
Project Management Office | 0 | 0 | 0 | 0 |  |  | 0 | Any missing rows indicate all values are 0
Systems Engineering | 0 | 0 | 0 | 0 |  |  | 0 | Any missing rows indicate all values are 0
Telescope & Site | 0 | 0 | 0 | 0 |  |  | 0 | Any missing rows indicate all values are 0
Totals | 0 | 0 | 0 | 0 |  |  | 0 | Totals | 0
Subsystem

## Table 3
Table 3
Top Risks List
Sort Number | Risk ID (Parent) | Subsystem | WBS | Risk Title | Probability Weighted Cost Exposure ($K) | Probability Weighted Cost Exposure After Mitigation ($K)
1
2
3
4
5
6
7
8
9
10
| Date: | 2020-09-02 |  | Top Ten Total: | 0 | 0

## Table 4
Table 4
Top 10 List - Opportunities
Sort Number | Opp ID # | Subsystem | WBS | Title | Probability Weighted Cost Exposure ($K)
1
2
3
4
5
6
7
8
9
10
| Date: | 2020-09-02 |  | Top Ten Total: | 0

## Table 6
Risk ID (Parent) | Subsystem | WBS | Summary | PWE ($K) | PWE After Mitigation ($K) | Proposed Management Response

## Table 7
Subsystem | Risk ID (Parent) | Summary | WBS | Trigger Date | Probability | Nonlabor Cost | Labor Cost | PWE ($K) | PWE After Mitigation ($K)

## Table 8
Subsystem | ID | Summary | Date | User | Comment

## Table 9
ID | Date | Author | Field | From | To

## Fig. 1 Running Graph
Date | PMO | DM | T&S | EPO | SE | Total | Top 50
2014-05-16 | 4142 | 14005 | 13925 | 1056 | 4120 | 37248
2014-08-06 | 5669 | 14273 | 13925 | 1056 | 4602 | 39525
2014-08-07 | 6372 | 14273 | 13925 | 1056 | 4894 | 40520
2015-02-24 | 6372 | 14273 | 14142 | 1056 | 7593 | 43436
2015-03-31 | 6372 | 14643 | 14223 | 1056 | 7116 | 43410
2015-04-28 | 6372 | 14799 | 14211 | 1056 | 7116 | 43554
2015-05-26 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7116.1 | 43286.15
2015-06-30 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7116.1 | 43286.15
2015-07-28 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7375.3 | 43545.35
2015-08-25 | 5877.23 | 14799.12 | 14438 | 1055.7 | 7664.2 | 43834.25
2015-09-29 | 5877.23 | 14164.22 | 14438 | 1055.7 | 7664.2 | 43199.35
2015-10-27 | 6700.53 | 14083.37 | 16195.7 | 1085.7 | 7664.2 | 45729.5
2015-11-24 | 6700.53 | 14746.23 | 16191.3 | 1085.7 | 7444.2 | 46167.96
2015-12-29 | 6700.53 | 17409.23 | 16416.3 | 1085.7 | 7634.2 | 49245.96
2016-01-20 | 6701 | 17409 | 16031 | 1086 | 7332 | 48559
2016-02-05 | 5801 | 17409 | 16031 | 1054.9 | 7334.2 | 47630.1
2016-02-29 | 5801 | 17409 | 16031 | 1054.9 | 7334.2 | 47630.1
2016-03-31 | 5801 | 17409 | 16031 | 1055 | 7284 | 47580
2016-04-26 | 5801 | 17409 | 16031 | 1055 | 7284 | 47580
2016-06-01 | 5801 | 17563.98 | 14616.98 | 1055 | 7277.75 | 46314.71
2016-06-06 | 5801 | 17564 | 14971 | 1055 | 7278 | 46669
2016-07-20 | 5442 | 17670 | 15130 | 1149 | 6747 | 46138
2016-10-07 | 5850 | 17670 | 15130 | 1233 | 7250 | 47133
2016-10-31 | 5850 | 17670 | 13642 | 894 | 7250 | 45306
2016-11-29 | 5850 | 22829 | 14790 | 1017 | 7339 | 51825
2017-01-06 | 6180.75 | 22829 | 14790 | 1017 | 8825.95 | 53642.7
2017-01-31 | 6180.75 | 22829 | 14366.33 | 933.77 | 8825.95 | 53135.8
2017-02-28 | 6180.75 | 22602.28 | 14662.33 | 933.77 | 8729.75 | 53108.88
2017-04-27 | 6180.75 | 22602.28 | 13633.4 | 875.97 | 8729.75 | 52022.15
2017-06-05 | 6180.75 | 12003.9 | 12801.8 | 875.97 | 9889.85 | 41752.27
2017-08-11 | 7601 | 12003.9 | 12050 | 1046 | 11819 | 44519.9
2017-10-09 | 7601 | 12000 | 11985 | 1014 | 11832 | 44432
2017-12-30 | 7601 | 11782 | 12726 | 747 | 12947 | 45803
2018-02-28 | 7601 | 11923 | 12726 | 701 | 12947 | 45898
2018-03-29 | 7601 | 12866 | 12942 | 1259 | 13586 | 48254
2018-05-07 | 9616 | 12866 | 12942 | 1182 | 13586 | 50192
2018-05-08 | 9616 | 12866 | 12942 | 1182 | 9210 | 45816 | 37052
2018-05-18 | 9616 | 12866 | 10977 | 1099 | 9210 | 43768 | 37052
2018-07-27 | 8935 | 12866 | 10977 | 1099 | 9210 | 43087 | 35160
2018-11-01 | 8683 | 11920 | 8599 | 1047 | 9210 | 39459 | 32000
2018-12-01 | 8683 | 11920 | 8598 | 1047 | 9162 | 39410 | 32000
2018-12-21 | 8683 | 11920 | 8598 | 1047 | 9162 | 39410 | 32000
2019-02-11 | 8683 | 10646 | 8869 | 1047 | 6372 | 35617 | 32000
2019-03-12 | 9871 | 9127 | 6557 | 551 | 4411 | 30517 | 29854
2019-04-02 | 9430 | 8942 | 6557 | 551 | 4411 | 29891 | 27567
2019-05-06 | 9430 | 8772 | 6557 | 551 | 4326 | 29636 | 27567
2019-06-06 | 9430 | 8441 | 6557 | 551 | 4168 | 29147 | 27567
2019-07-01 | 9430 | 8379 | 6163 | 551 | 4168 | 28691 | 26868
2019-08-02 | 6774 | 8256 | 5487 | 530 | 3280 | 24327 | 22746
2019-09-09 | 6774 | 8188 | 4592 | 530 | 3221 | 23305 | 21912.56
2019-12-03 | 6774 | 7729 | 4439 | 530 | 3218 | 22690 | 21592
2020-02-04 | 6774 | 7668 | 4431 | 530 | 3578 | 22981 | 21951.78
2020-03-03 | 6774 | 7581 | 4086 | 530 | 3578 | 22549 | 21844.68
2020-04-03 | 6476 | 7554 | 4041 | 530 | 3513 | 22114 | 21712
2020-05-01 | 6476 | 7554 | 4041 | 530 | 3513 | 22114 | 21623
2020-06-01 | 6476 | 6765 | 4041 | 530 | 3769 | 21581 | 21142
2020-07-01 | 6476 | 5986 | 4041 | 567 | 3769 | 20839 | 20449
2020-08-05 | 6476 | 7175 | 4184 | 567 | 3769 | 22171 | 21640.78
2020-09-02 | 6476 | 5591 | 4121 | 567 | 3769 | 20524 | 20102